## Timeline
ANALYSTLAB AFRICA - Experience Lab Internship Programme (Project Management Track)
HIGH-LEVEL TIMELINE - HealthConnect Clinic Experience Lab
Project Manager: Devinci Ebaha Djoki ¦ Sponsor: AnalystLab Africa ¦ Document Version 1.0
Section A : Week 4 Detailed Schedule (Confirmed by the assignment brief)
WBS Code | Task | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Status
1.1.1 | Review HealthConnect business scenario, central project question, and project resources | [7 empty] | Confirmed
1.1.2 | Identify and review PM-track-relevant tools and resources | [7 empty] | Confirmed
1.1.3 | Draft Project Brief / Charter | [7 empty] | Confirmed
1.1.10 | Establish initial coordination touchpoint with the four technical tracks | [7 empty] | Confirmed
1.1.4 | Draft Scope Statement | [7 empty] | Confirmed
1.1.5 | Draft Stakeholder Register | [7 empty] | Confirmed
1.1.6 | Draft Work Breakdown Structure | [7 empty] | Confirmed
1.1.7 | Draft High-Level Timeline | [7 empty] | Confirmed
1.1.8 | Draft Initial Risk and Dependency Register | [7 empty] | Confirmed
1.1.9 | Draft Communication Approach | [7 empty] | Confirmed
1.1.11 | Compile the 7 governance deliverables into the Project Initiation Package | [7 empty] | Confirmed
1.1.12 | Draft Week 4 Project Summary | [7 empty] | Confirmed
1.1.13 | Organize and upload Week 4 files to the designated Google Drive folder | [7 empty] | Confirmed
1.1.14 | Update GitHub repository and README.md with Week 4 progress | [7 empty] | Confirmed
Days are relative working days within Week 4 (Day 1 = start of week, Day 7 = Sunday submission deadline, 11:59 PM WAT). No official day-by-day calendar has been issued by the programme; only the Week 4 submission deadline is confirmed. This day-level sequencing is a Project Manager scheduling assumption, not a programme-confirmed date.
Section B : Programme-Level Overview, Weeks 4-8 (Week 4 confirmed; Weeks 5-8 assumed)
WBS Code | Phase / Task | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Status
1.1 | Problem Understanding | [5 empty] | Confirmed
1.2 | Analysis and Solution Design | [5 empty] | Assumed
1.2.1 | Continue cross-track coordination; consolidate analysis/design outputs | [5 empty] | Assumed
1.2.2 | Update risk and dependency register based on Week 4 outcomes | [5 empty] | Assumed
1.2.3 | Produce Week 5 Project Summary | [5 empty] | Assumed
1.3 | Development | [5 empty] | Assumed
1.3.1 | Track cross-team development progress | [5 empty] | Assumed
1.3.2 | Manage risks/blockers surfaced during development | [5 empty] | Assumed
1.3.3 | Produce Week 6 Project Summary | [5 empty] | Assumed
1.4 | Testing and Refinement | [5 empty] | Assumed
1.4.1 | Coordinate review/testing feedback across tracks | [5 empty] | Assumed
1.4.2 | Produce Week 7 Project Summary | [5 empty] | Assumed
1.5 | Final Presentation | [5 empty] | Assumed
1.5.1 | Consolidate all track contributions into a final narrative | [5 empty] | Assumed
1.5.2 | Coordinate final presentation preparation | [5 empty] | Assumed
1.5.3 | Produce project closeout summary | [5 empty] | Assumed
Weeks 5-8 reflect the planning assumption of one phase per week stated in the Project Charter, Scope Statement, and Work Breakdown Structure (risk R4 in the Risk and Dependency Register). This mapping is not explicitly confirmed by the assignment brief and will be revised once the programme issues an official detailed calendar.
Legend
Confirmed (Week 4, per assignment brief)
Assumed (Weeks 5-8, planning hypothesis)
Notes
- This timeline is consistent with the Work Breakdown Structure (WBS): every WBS 1.1.x work package appears in Section A, and phases 1.2 through 1.5 in Section B mirror the WBS decomposition exactly.
- The coordination touchpoint (1.1.10) is scheduled early in Week 4 (Day 2), immediately after the Charter is drafted, consistent with the early-alert mitigation defined for risk R1 in the Risk and Dependency Register.
- Only Week 4 (Section A and the Week 4 column of Section B) is confirmed by the assignment brief; all other weeks are a Project Manager planning assumption and will be adjusted once the programme communicates an official calendar.